## Time Sheet
Feedback Management System
Daily Time Sheet for : Employee Name | Abhishek Goyal |  | Timesheet_75891 |  | October
Task Desc |  | Task Category | W | T | F | S | S | M | T | W | T | Total
| Phase |  | 1 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Available Hrs |  |  | 1 | 8 | 6 | 0 | 0 | 6 | 6 | 8 | 7 | 42
Over Time |  |  | 1 | 0 | 0 | 16 | 0 | 0 | 0 | 3 | 0 | 20
Total Hrs. |  |  | 1 | 8 | 6 | 16 | 0 | 6 | 6 | 11 | 7 | 61
Reqiurment Analysis | Requirements | Meeting | Timesheet_75891 T 16: 2 | 2
Preparing understanding Document & Reverse Presentation | Requirements | Main Task(Prep.) | [9 empty] | 1 | bar: Timesheet_75891 T 16
Preparing QTS | Requirements | Main Task(Prep.) | Timesheet_75891 T 16: 2 | 2
Team Meeting | Requirements | Main Task(Prep.) | [9 empty] | 1 | bar: Timesheet_75891 T 16
Understanding HLD/Class Diagram Prep | Requirements | Meeting | Timesheet_75891 T 16: 2 | 2
0
HLD Preparation | High Level Design | Main Task(Prep.) | [9 empty] | 1 | bar: October S 18
HLD Review | High Level Design | Review | [9 empty] | 1 | bar: October S 18
HLD Rework | High Level Design | Rework | [9 empty] | 1 | bar: October S 18
0
LLD Prepration | Low Level Design | Main Task(Prep.) | October S 18: 2 | 2
LLD Review | Low Level Design | Review | [9 empty] | 1 | bar: October S 18
LLD Rework | Low Level Design | Rework | [9 empty] | 0
0
Coding | Coding | Main Task(Prep.) | October S 18: 4 | 4
0
0
Coding | Coding | Main Task(Prep.) | [9 empty] | 1 | bar: October M 20
0
Coding | Coding | Main Task(Prep.) | [9 empty] | 1 | bar: October T 21
0
Self testing | Unit Testing | Review | [9 empty] | 1 | bar: October W 22
Rework | Coding | Rework | October T 23: 2 | 2
0
Team Meeting | Coding | Meeting | [9 empty] | 0
Code peer review | coding | Review | [9 empty] | 0
Code peer review | Coding | Review | [9 empty] | 0
0
0
Test result review | Unit Testing | Review | [9 empty] | 0
Test result review | Unit Testing | Rework | [9 empty] | 0
0
Team Meeting | Coding | Meeting | [9 empty] | 0
Code integration | Coding | Review | October W 22: 2 | 2
Integration testing | Integration Testing | Rework | October W 22: 3 | 3
Review | Integration Testing | Review | [9 empty] | 0
Test result review | Integration Testing | Review | [9 empty] | 0
0
Application Integration | Integration Testing | Rework | [9 empty] | 0
PLP presentation | Miscellaneous | Main Task(Prep.) | [9 empty] | 0
0
0
| Project Management | Main Task(Prep.) | [9 empty] | 0
| Integration Testing | Review | [9 empty] | 0
| Integration Testing | Meeting | [9 empty] | 0
0
0
| Config Management | Main Task(Prep.) | [9 empty] | 0
| Config Management | Rework | [9 empty] | 0
| Config Management | Meeting |  |  | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 3
0
Lunch,tea break | Miscellaneous |  |  |  | 1.5 | 1.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 5
L1 preparation | Miscellaneous |  |  |  | 4 | 4 |  | 4 | 4 | 4 | 4 | 24
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Company Internal
Note on M2: Month Start Date. Please enter Month start date. (e.g. 01 Aug 02)
Note on M7: Total Effort for the Month

## Effort Summary
Consolidated Timesheet
|  | TASK | TASK | REVIEW | REWORK | MEETING |  |  | Appraisal | Audits | Holiday | Leave | Meeting | Organization Initiatives | Others | Proposal/ Contract
|  | 1 |  | 3 | 4 | 2 |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Requirements | M | 4 | 8 | 0 | 0 | 4 | Miscellaneous | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
High Level Design | D | 1 | 1 | 1 | 1 | 0
Low Level Design | H | 2 | 2 | 1 | 0 | 0
Coding | B | 6 | 6 | 2 | 2 | 0
Unit Test Planning | Q | 0 | 0 | 0 | 0 | 0
Unit Testing | R | 0 | 0 | 1 | 0 | 0
Integration Test Planning | F | 0 | 0 | 0 | 0 | 0
Integration Testing | G | 0 | 0 | 0 | 3 | 0
System Test Planning | N | 0 | 0 | 0 | 0 | 0
System Testing | O | 0 | 0 | 0 | 0 | 0
Acceptance Testing | A | 0 | 0 | 0 | 0 | 0
Implementation & Warranty | E | 0 | 0 | 0 | 0 | 0
Release | L | 0 | 0 | 0 | 0 | 0
Project Management | K | 0 | 0 | 0 | 0 | 0
Config Management | C | 0 | 3 | 0 | 0 | 3
Training | P | 0 | 0 | 0 | 0 | 0
Project Improvements | J | 0 | 0 | 0 | 0 | 0
Company Internal

## Rev. History
Date | Version # | Sections Changed | Details of changes made | Approved by
2016-05-19 | 1 | Main Task(Prep.) | Documents Prepared | Tanmaya K Acharya
Company Internal

## Consolidated Data (hidden)
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Reqiurment Analysis | Requirements | Meeting | M | 2 | M2 | 2
Preparing understanding Document & Reverse Presentation | Requirements | Main Task(Prep.) | M | 1 | M1 | 1
Preparing QTS | Requirements | Main Task(Prep.) | M | 1 | M1 | 2
Team Meeting | Requirements | Main Task(Prep.) | M | 1 | M1 | 1
Understanding HLD/Class Diagram Prep | Requirements | Meeting | M | 2 | M2 | 2
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
HLD Preparation | High Level Design | Main Task(Prep.) | D | 1 | D1 | 1
HLD Review | High Level Design | Review | D | 3 | D3 | 1
HLD Rework | High Level Design | Rework | D | 4 | D4 | 1
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
LLD Prepration | Low Level Design | Main Task(Prep.) | H | 1 | H1 | 2
LLD Review | Low Level Design | Review | H | 3 | H3 | 1
LLD Rework | Low Level Design | Rework | H | 4 | H4 | 0
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
Coding | Coding | Main Task(Prep.) | B | 1 | B1 | 4
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
Coding | Coding | Main Task(Prep.) | B | 1 | B1 | 1
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
Coding | Coding | Main Task(Prep.) | B | 1 | B1 | 1
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
Self testing | Unit Testing | Review | R | 3 | R3 | 1
Rework | Coding | Rework | B | 4 | B4 | 2
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
Team Meeting | Coding | Meeting | B | 2 | B2 | 0
Code peer review | coding | Review | B | 3 | B3 | 0
Code peer review | Coding | Review | B | 3 | B3 | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
Test result review | Unit Testing | Review | R | 3 | R3 | 0
Test result review | Unit Testing | Rework | R | 4 | R4 | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
Team Meeting | Coding | Meeting | B | 2 | B2 | 0
Code integration | Coding | Review | B | 3 | B3 | 2
Integration testing | Integration Testing | Rework | G | 4 | G4 | 3
Review | Integration Testing | Review | G | 3 | G3 | 0
Test result review | Integration Testing | Review | G | 3 | G3 | 0
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
Application Integration | Integration Testing | Rework | G | 4 | G4 | 0
PLP presentation | Miscellaneous | Main Task(Prep.) | I | 8 | I8 | 0
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | Project Management | Main Task(Prep.) | K | 1 | K1 | 0
0 | Integration Testing | Review | G | 3 | G3 | 0
0 | Integration Testing | Meeting | G | 2 | G2 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | 0 |  | #N/A | #N/A | #N/A | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | Config Management | Main Task(Prep.) | C | 1 | C1 | 0
0 | Config Management | Rework | C | 4 | C4 | 0
0 | Config Management | Meeting | C | 2 | C2 | 3
0 | 0 |  | #N/A | #N/A | #N/A | 0
Lunch,tea break | Miscellaneous |  | I | #N/A | #N/A | 5
L1 preparation | Miscellaneous |  | I | #N/A | #N/A | 24
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
0 | 0 | 0 | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0
0 | 0 |  | #N/A | #N/A | #N/A | 0

## Constants (hidden)
Requirements | Main Task(Prep.) | Requirements | Acceptance Testing | A | Main Task(Prep.) | 1 | Appraisal | 5
High Level Design | Review | High Level Design | Coding | B | Meeting | 2 | Audits/QF | 6
Low Level Design | Rework | Low Level Design | Config Management | C | Review | 3 | Holiday | 7
Coding | Meeting | Coding | High Level Design | D | Rework | 4 | Leave | 8
Unit Test Planning |  | Unit Test Planning | Implementation & Warranty | E |  |  | Meeting | 9
Unit Testing |  | Unit Testing | Integration Test Planning | F |  |  | Organization Initiatives | 10
Integration Test Planning |  | Integration Test Planning | Integration Testing | G |  |  | Others | 11
Integration Testing |  | Integration Testing | Low Level Design | H |  |  | Proposal/ Contract | 12
System Test Planning |  | System Test Planning | Miscellaneous | I
System Testing |  | System Testing | Project Improvements | J
Acceptance Testing |  | Acceptance Testing | Project Management | K
Implementation & Warranty |  | Implementation & Warranty | Release | L
Release |  | Release | Requirements | M
Project Management |  | Project Management | System Test Planning | N
Config Management |  | Config Management | System Testing | O
Training |  | Training | Training | P
Project Improvements |  | Project Improvements | Unit Test Planning | Q
Miscellaneous | Appraisal | Miscellaneous | Unit Testing | R
Audits/QF
Holiday
Leave
Meeting
Others
Organization Initiatives
Proposal/ Contract

## Timesheet Data (hidden)
Activity | Activity | Holiday Date | Holiday Date
0 |  | 2005-01-14 | 2005-01-14
Analysis | Analysis | 2005-01-26 | 2005-01-26
Audit | Audit | 2005-03-25 | 2005-03-25
Coding | Coding | 2005-04-14 | 2005-04-14
Config.Mgmt | Config.Mgmt | 2005-04-22 | 2005-04-22
Documentation | Documentation | 2005-08-15 | 2005-08-15
EIP Time entry | EIP Time entry | 2005-08-26 | 2005-08-26
ERT | ERT | 2005-09-07 | 2005-09-07
GB activity | GB activity | 2005-10-12 | 2005-10-12
GB meeting | GB meeting | 2005-11-01 | 2005-11-01
Idle Time | Idle Time | 2005-12-26 | 2005-12-26
Link down | Link down
LUT | LUT
Meeting | Meeting
Metrics Report | Metrics Report
Mgmt | Mgmt
Onsite Call | Onsite Call
Orgnz Activity | Orgnz Activity
Others | Others
Peer Review Code | Peer Review Code
Peer Review LUT | Peer Review LUT
Peer Review Testing | Peer Review Testing
QC Activity | QC Activity
QC Code Review | QC Code Review
QC Co-ordination | QC Co-ordination
QC Documentation | QC Documentation
QC LUT/UTP Review | QC LUT/UTP Review
QC Testing | QC Testing
Query clarification | Query clarification
Rework-External | Rework-External
Rework-Internal | Rework-Internal
Team Meeting | Team Meeting
Technical Coordination | Technical Coordination
Test Data Setup | Test Data Setup
Testing | Testing
Training | Training
Waiting for ERT | Waiting for ERT
Waiting for Onsite | Waiting for Onsite
Waiting for QC | Waiting for QC
Waiting for Query reply. | Waiting for Query reply.