## Sheet1
PLP High Level Work Breakdown structure
Date | Day | Day | Activity | Deliverables | Phase
2018-10-16 | Tuesday | Day-1 | 1. Understand the Highlevel WBS, PLP phases and artifacts | 1. Detailed WBS | Requirement
|  |  | 2. Create project folder structure in SVN and learn working with SVN | 2. Understanding document
|  |  | 3. Prepare WBS | 3. Updated Query Tracking Sheet
|  |  | 4. Update Query tracking sheet. | 4. Minutes of Meeting(one sample)
5. Minutes of Meeting
2018-10-17 | Wed | Day-2 | 1. Presentation/update of understanding document to Mentor. | 1. Usecase, Class diagram | Design
|  |  | 2. Modify Class Diagram | 2. Sequence diagram (one sample)
|  |  | 3. Create usecase and sequence diagram | 3. DB design
|  |  | 4. DB Design and Screen Shots. | 4. Screens shots
|  |  | LLD Preparation. | 5. Updated WBS
|  |  | 1. Add functionality ,CTQ, nonfunctional test cases | 1. UTP(for one module only)
2. LLD
3. Traceability Matrix.(one module sample)
2018-10-18 | Thursday | Day-3 | Coding & Unit Testing(self testing) | Code | Coding
2018-10-22 | Monday | Day-4 | Coding & Unit Testing(self testing) | code | Coding / Review
code
Updated review report
Defect tracking sheet
2018-10-23 | Tuesday | Day-5 | Presentation | 1. Updated wbs | Presentation
2. Updated Query Tracking sheet
3. Use case Digram,Unders doc
3. HLD(CD,sq diagram,screens,DB)
4. LLD
5.Updated UTP
6.Traceability matrix
6 Updated review report and
7.Defect tracking sheet
8.Updated Timesheet
9.MoM(one sample)
10.deployed application(war)
11. Presentation PPT