## Project Profile
Defect Tracking Sheet
Project Code | Group2
Project Name | Feedback Management System
Prepared/Modified by | Role | Date of Preparation
Abhishek Goyal |  | 22/10/2018
Reviewed by | Role | Date of Review
Myneni Sai Eshwar |  | 22/10/2018
Approved by | Role | Date of Approval
Tanmay K Acharya
Circulation List | sai-eshwar.myneni@capgemini.com rohit.b.agrawal@capgemini.com abhishek.ay.kumar@capgemini.com abhishek.b.goyal@capgemini.com payyavula.bhavasagar@capgemini.com snehasagari.bandarupalli@capgemini.com | Version Number of the template: 1.1
Version Number | 1

## Defect Tracking Sheet
Project ID: | Group 1 | Project Name : | Airline Reservation System | [22 empty] | VERIFIED
CLOSED
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments |  | REOPENED | Coding |  |  | Internal Dev
D_01 | Feedback Participant | No validation on ratings. | As textbox is used the particpant can fill any number for rating. No UI validation done for that | Coding | Chrome | Eclipse | P2 | High | 1 | 1 | 19/10/2018 | Sneha | Abhishek Goyal | CLOSED | PPR | NA | Abhishek Goyal | 20/10/2018 | 20/10/2018 | Sneha | 1 | 1 | NA | NA | SR | CNR | New Requirement | P2 | High | External QA
D_02 | Coordinator | Course duration not validated against start and end date | The course start date & end date difference should be equal to course duration | Coding | Chrome | Eclipse | P2 | High | 1 | 1 | 19/10/2018 | Sneha | Abhishek Kumar | CLOSED | PPR | NA | Abhishek Kumar | 20/10/2018 | 20/10/2018 | Sneha | 1 | 1 | NA | NA | RT | REP | Documentation | Low
D_03 | Feedback Participant | Submission resulted in error as the feedback was already submitted | There should be check for what courses are assigned and for which feedback is pending. | Coding | Chrome | Eclipse | P2 | High | 1 | 1 | 19/10/2018 | Sneha | Abhishek Goyal | CLOSED | PPR | NA | Abhishek Goyal | 20/10/2018 | 20/10/2018 | Sneha | 1 | 1 | NA | NA | RT | REP | Documentation | Low

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By